## Sheet1
id | group | content | title | start | end
1 | cvml | cvml adapted to master_grid | Ryan, Su | 2018-05-15 | 2018-05-31
2 | Imagery | Download/mask Planet (Meridia sites) | Tammy, Ron | 2018-05-15 | 2018-05-31
3 | Imagery | Download/mask Planet (Ghana) | Tammy, Ron | 2018-06-01 | 2018-07-31
4 | Media | Project website and materials | Lyndon | 2018-05-15 | 2018-06-15
5 | mapper | mapper upgrades - png overlay | Dennis | 2018-05-15 | 2018-05-31
6 | mapper | mapper upgrades - classify features | Dennis | 2018-05-15 | 2018-05-31
7 | mapper | mapper upgrades - point labelling | Dennis | 2018-06-01 | 2018-06-15
8 | mapper | mapper upgrades - stop intersects, snapping, etc |  | 2018-06-01 | 2018-06-30
9 | mapper | daemons - mapper send/receive | Lei | 2018-06-01 | 2018-06-15
10 | cvml | daemons - cvml send/receive | Su, Ryan, Lei | 2018-06-01 | 2018-06-15
11 | mapper | Upgrade/update Q/I sites | Lei | 2018-05-15 | 2018-06-15
12 | mapper | Finalize Q merge/label method | Lei, Ryan | 2018-05-15 | 2018-06-15
13 | cvml | Update RF method to match labels | Su, Ryan | 2018-05-15 | 2018-06-15
14 | mapper | SpatialCollective onboard | Lyndon | 2018-06-01 | 2018-06-15
15 | mapper | SpatialCollective testing | Lyndon | 2018-06-15 | 2018-06-30
16 | Interactivity | Interactivity testing | All | 2018-07-01 | 2018-07-15
17 | Interactivity | Alpha tuning/mapping 5000 km^2 | All | 2018-07-15 | 2018-08-24
18 | Segment | MaskRCNN test | Ryan | 2018-07-01 | 2018-08-24
19 | Segment | On RF posterior probs | Ron | 2018-07-01 | 2018-08-24